## Sheet1
Title (이슈제목) | Issue_Details (상세 내용) | Action_Result (조치결과) | Cause (근본원인) | Preventive_measures (향후 개선 방향)
Machine Failure | The main motor stopped working suddenly. | Replaced the motor. | Wear and tear of the motor. | Implement regular maintenance checks.
Overheating | The system temperature exceeded safe levels. | Installed additional cooling systems. | Inadequate cooling systems. | Upgrade cooling infrastructure.
Power Outage | Unexpected power cut during operation. | Restored power and resumed operations. | External power grid failure. | Install backup power systems.
System Crash | The system crashed during peak usage. | Rebooted the system and applied updates. | System overload due to high traffic. | Increase system capacity and robustness.
Network Issue | Intermittent network connectivity issues. | Diagnosed and fixed network issues. | Router malfunction. | Regularly check and maintain network equipment.
Data Loss | Important data files were lost. | Recovered data from backup. | Accidental deletion of files. | Implement better data management practices.
Software Bug | A bug in the application caused incorrect calculations. | Patched the software bug. | Flaw in the algorithm. | Conduct thorough testing before deployment.
Hardware Malfunction | A hardware component failed to initialize. | Replaced the faulty hardware. | Defective hardware component. | Use higher quality components.
Security Breach | Unauthorized access to the system was detected. | Strengthened security measures. | Weak security protocols. | Implement multi-factor authentication.
High Latency | Significant delay in response time. | Optimized the code for better performance. | Inefficient code. | Conduct code reviews and performance testing.
Memory Leak | Memory usage kept increasing, causing slowdowns. | Fixed the memory leak issue. | Unreleased memory in the application. | Regularly monitor memory usage.
Disk Corruption | Disk errors caused data corruption. | Repaired the disk and restored data. | Physical damage to the disk. | Implement better disk management practices.
Incorrect Output | The output results were incorrect. | Corrected the software logic. | Logical error in the code. | Enhance software testing procedures.
Resource Exhaustion | System resources were completely used up. | Freed up resources and optimized usage. | Resource-intensive processes. | Monitor resource usage and optimize.
Configuration Error | Incorrect system configuration led to failures. | Reconfigured the system settings. | Misconfiguration during setup. | Double-check configurations before applying.